## Summary
Social Media user story

	Project name:	Ultimate QA – Practice		Priority	High
	Sprint	2		Product Quality
	Start date:	12-Jul-24		Number of Tcs	6
	Release date:	26-Jul-24
	QA Lead:
	QC members:	Ly.Cao

No	Test Type	Priority / (Risk-based testing)	Quality	Person In Charge	TEST RESULT
					Not run yet	FAILED	BLOCKED	Passed	Pending	TOTAL
1	Functionality	Medium		Ly.Cao	14	0	0	1	0	15
2	UX	Medium			3	0	0	0	0	3
					17	0	0	1	0	18
	QUALITY
	LOW	Having at least 1 BLOCKER issue
	Medium	Having at least 1 Critical issue
	GOOD	Having no Blocker/ Critical issue

## Functionality
Functionality Test cases for Social Media user story
					Number of Failed HIGH priority test case	0
	NOT RUN YET	14		PASSED	1				PASSED	0
	FAILED	0		PENDING	0
	BLOCKED	0		TOTAL	15				PENDING	0
					TOTAL	5
					Test Result
No	Summary	Priority	Auto?	Notes	Chrome	FF	Microsoft Edge	Notes for execution	Notes	Tester
1	Verify clicking on each X icons successfully redirects the user to https://x.com/Nikolay_A00	HIGH	Yes	Steps: / 1. Access Complicated page / 2. Scroll down to ‘Section of Social Media Follows’ / 3. Click on the first X / Expected result: / - System navigates to https://x.com/Nikolay_A00 / Notes / - Repeat step #1 – step 3 for remaining X icons	Passed
2	Verify clicking on each F icons successfully redirects the user to https://www.facebook.com/Ultimateqa1/	HIGH	Yes	Steps: / 1. Access Complicated page / 2. Scroll down to ‘Section of Social Media Follows’ / 3. Click on the first F / Expected result: / - System navigates to https://www.facebook.com/Ultimateqa1/ / Notes / - Repeat step #1 – step 3 for remaining F icons
3	Ensure that automation testers can uniquely identify and interact with each X icon	HIGH	Yes	Expected result: / - Automation tester can create a script to verify that 5 X icons are present. / - Automation tester can create a script to click on each icons correctly
4	Ensure that automation testers can uniquely identify and interact with each F icon	HIGH	Yes	Expected result: / - Automation tester can create a script to verify that 5 F icons are present. / - Automation tester can create a script to click on each icons correctly
5	System navigates to /complicated-page successfully when clicking on ‘Big page with many elements’ link	HIGH	No

## UX
UX Test cases for Social Media user story
'					Number of Failed HIGH priority test case	0
	NOT RUN YET	3		PASSED	0				PASSED	0
	FAILED	0		PENDING	0				PENDING	0
	BLOCKED	0		TOTAL	3				TOTAL	2

					Test Result
No	Summary	Priority	Auto?	Notes	Chrome	FF	Microsoft Edge	Notes for execution	Test Result	Notes	Tester
1	Verify GUI of 'Section of Social Media Follows' displays as the design	HIGH	No	Expected result: / - Section of Social Media Follows / - Front size, font color, align and position are the same as the design / Notes: Cannot check position of a field on automation test script	Passed
2	Verify website layout and content are optimized for different devices and screen sizes.	Medium	No

## General Checklist
General checklist

No	Summary	Priority
GUI Verifying				String	Summary	Test data	Priority
1	Verify header	HIGH			English	Hello	HIGH
2	Verify item name included in screen	HIGH			Hebrew	שלום	Medium
3	Verify type of items on screen	HIGH			Mixed	123 Hello שלום	Medium
4	Verify icon	HIGH			Url	https://translate.google.com/#en/iw/Hello	Low
5	Verify layout (position of fields, background)	HIGH			SQL	Select * from * where 1=1	Low
6	Verify font type, font size, color	HIGH			Html	<script src="https://www.gstatic.com/firebasejs/4.9.0/firebase-app.js"></script>	Low
1	Verify footer	HIGH
Field validation (String)
1	Verify if user is able to input both text and number. See test data sheet	HIGH		Number
2	Verify user is NOT able to copy & paste an image	Medium
3	Verify user can't input > max length	Medium
4	Verify warning message when input < min length	Medium
5	Verify user can't input spaces, no quotes, no commas, no brackets, no <> signs	Medium
6	Verify user can't leave blank for required field	HIGH
Field validation (number: Integer)
1	Verify if user is able to input integer only	HIGH
2	Verify user is NOT able to copy & paste an image, string, url,...	Medium
3	Verify user can't input > max length	Medium
4	Verify warning message when input < min value	Medium
5	Verify warning message when input > max value	Medium
6	Verify user can't leave blank for required field	HIGH
Field validation (number: Float)
1	Verify if user is able to input both integer & float	HIGH
2	Verify user is NOT able to copy & paste an image, string, url,...	Medium
3	Verify user can't input > max length	Medium
4	Verify warning message when input < min value	Medium
5	Verify warning message when input > max value	Medium
6	Verify user can't leave blank for required field	HIGH
Combo box
1	Verify able to select an item from combo box list	Medium
2	Verify message on when network is weak	Medium
3
4
Network
1	Verify message on screen when network is lost connection	Medium
2	Verify message on when network is weak	Medium
3
4